## Part1
Serial | Task Name | Sub Task | Deliverable | Assigned to | Start Date | End Date | Completion(%)
1 | Introduction |  | Introduction | Lorena Macias | 2021-02-18
1.1 | Purpose |  | Purpose | Phuc Le | 2021-02-18
1.2 | Scope |  | Scope | Phuc Le | 2021-02-18
1.3 | Definitions, Acronyms, and Abbreviations |  | Definitions | Dylan Nguyen | 2021-02-18 |  | 90%
1.4 | References |  | References | Omar Ramierez | 2021-02-18 | 2021-03-16 | 100%
1.5 | Overview |  | Overview | Omar Ramierez | 2021-02-18 | 2021-03-16 | 100%
2 | Architectural Representation |  | Representation | Jacob Powell | 2021-02-18 | 2021-03-20 | 100%
3 | Architectual Goals and Constraints |  | Goals and Constraints | Nathan Marcos | 2021-02-18 | 2021-03-20 | 100%
4 | Use-Case View |  | Use Cases | All | 2021-02-18
4.1 | Use-Case Diagrams |  | Use-Case Diagram | Dylan Nguyen | 2021-02-18 | 2021-03-13 | 100%
5 | Logical View |  |  |  | 2021-02-18
5.1 | Logical Overview | OSI Model |  | Kenneth Truong | 2021-02-18 | 2021-03-12 | 100%
5.2 | Architecurally Significant Design Packages | Package Diagram |  | Kenneth Truong | 2021-02-18 | 2021-03-22 | 100%
5.3 | Architecturally Significant Design Classes | Class Diagram |  | Jacob Powell | 2021-02-18 | 2021-03-23 | 100%
6.1 | Implementation/Development View | Implementation Diagram |  | Lorena Macias | 2021-02-18
7 | Process View | Process Diagram |  | Grant Marsh | 2021-02-18
8 | Deployment/Physical View | Deployment Diagram |  | Dylan Nguyen | 2021-02-18 | 2021-03-23 | 100%
9 | Data View (OPTIONAL) |  |  |  | 2021-02-18
10 | Size and Performance |  |  | Nathan Marcos | 2021-02-18 | 2021-03-22 | 100%
11 | Quality |  |  | Nathan Marcos | 2021-02-18 | 2021-03-22 | 100%
12 | Appendix A |  |  | Dylan Nguyen | 2021-03-23 | 2021-03-23 | 100%

## Part 2
Serial | Task Name | Sub Task | Deliverable | Assigned to | Start Date | End Date | Completion(%)
1 | Our Approach |  | Slide Completion | Lorena | 2021-04-29
2 | Design Development |  | Slide Completion | Dylan | 2021-04-29
3 | Division of work |  | Slide Completion | Dylan | 2021-04-29
4 | Key Challenges |  | Slide Completion | Dylan | 2021-04-29
5 | Artifacts |  | Slide Completion | Dylan | 2021-04-29
6 | Use Cases |  | Slide Completion | Omar | 2021-04-29
7 | Quality/Size and Performance | Update SAD for Security Requirements | Slide Completion | Nathan | 2021-04-29
8 | Functional Components |  | Slide Completion | Jacob, Grant | 2021-04-29
9 | Core Components |  | Slide Completion | Phuc, Kennth | 2021-04-29